## Documentation
Sheet | What it Contains
ps | This is the list of stories. It feeds the other sheets so any changes here will be replicated elsewhere. It is also the source of the mailmerge to generatethe cards.
ScoreBase | This is where the final score it tallied, simply put a 1 in the cell for each completed story by the team. Once the scores are entered, just delete the 1 in the Random column and this will update all the cells based on the random market conditions. Caution…Additional keystrokes will cause an updatge and you will get a new set of random number.
Print | This is to create a hardcopy record for the facilitate to test and record completed stories. Each iteration should do regression testing to record a complete test of all claimed features.
Score2011-05 | Run at Landmark with 90% of the group unfamiliar with software development.
Score2011-10 | Run at Landmark with 90% of the group unfamiliar with software development.
Score2012-01 | Run at the Houston Agile Leadership Network Summit. Note that this group had many managers and they not only required 1 extra iteration, but cdelivered much less functionality.

## ScoreBase
ID | Story | Value | Random | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6
1 | Build an animal | Must Have | 1
2 | Make an enclosure for the animal | Must Have
101 | Give the animal four legs | 300 | 1
102 | Make an enclosure for the animal. Animal must have egress | 500 | 1
103 | Make a transport with wheels for your animal | 300 | 1
104 | Give your animal wings | 300 | 1
105 | Give your animal a head | 500 | 1
106 | Make sure your animal has at least two eyes | 300 | 1
107 | Make your animal one color | 200 | 1
108 | Make your animal freestanding on two legs | 200 | 1
109 | Give your animal two arms | 200 | 1
110 | Give your animal horns | 200 | 1
111 | Give your animal antlers | 400 | 1
112 | Put a roof on the enclosure to cover the animal | 300 | 1
113 | Give your animal a trunk | 400 | 1
1
201 | Make a baby version of the animal | 500 | 1
202 | Give your animal stripes | 600 | 1
203 | Make a cart for the baby (or add a place for the baby on the transport) | 300 | 1
204 | Make the animal at least 10cm high | 400 | 1
205 | Make the animal at least 10cm long | 200 | 1
206 | Give your animal tusks or fangs | 300 | 1
207 | Enlarge your enclosure to take the baby | 400 | 1
208 | Make the enclosure at least 10 cm by 10 cm | 400 | 1
209 | Give the animal 6 legs | 400 | 1
210 | Give your animal a second head | 200 | 1
211 | Give your animal a tail | 100 | 1
212 | Give your animal a mouth | 300 | 1
1
301 | Put a gate on the enclosure to allow the animal egress | 200 | 1
302 | Make the enclosure at least 4 blocks high | 200 | 1
400 | Aesthetics | 2000 | 1
|  |  | Base | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final | 0 | 0 | 0 | 0 | 0 | 0
Rank | bar: Team 1 to Team 6

## ps
Defect ID | Defect Type | Status/State Desc | Subject | Product | Version | Comp Level 1 | Severity | Priority | Fix Target | Reported By | Assigned To | Date Reported | PEF | Fixed On | Closed On | Fixed Build/cycle | Fixed Version | Additional Info | Additional Info
1 |  |  | Build an animal |  |  | Must Have | [12 empty] | It looks like an animal
2 |  |  | Make an enclosure for the animal |  |  | Must Have | [12 empty] | The animal fits in the enclosre and has egress
101 |  |  | Give the animal four legs |  |  | 300 | [12 empty] | The animal has exactly 4 legs
102 |  |  | Make an enclosure for the animal. Animal must have egress |  |  | 500 | [12 empty] | The animal fits in the enclosre and has egress
103 |  |  | Make a transport with wheels for your animal |  |  | 300 | [12 empty] | The animal (all supporting legs) fit on the transport
104 |  |  | Give your animal wings |  |  | 300 | [12 empty] | The animal has wings
105 |  |  | Give your animal a head |  |  | 500 | [12 empty] | The animal has a head
106 |  |  | Make sure your animal has at least two eyes |  |  | 300 | [12 empty] | the animal has at least 2 eyes
107 |  |  | Make your animal one color |  |  | 200 | [12 empty] | The animal body, head,and legs are made of one color
108 |  |  | Make your animal freestanding on two legs |  |  | 200 | [12 empty] | The animal can freely stand on 2 legs.
109 |  |  | Give your animal two arms |  |  | 200 | [12 empty] | The animal has 2 arms
110 |  |  | Give your animal horns |  |  | 200 | [12 empty] | The animal has horns
111 |  |  | Give your animal antlers |  |  | 400 | [12 empty] | The animal has antlers
112 |  |  | Put a roof on the enclosure to cover the animal |  |  | 300 | [12 empty] | The enclosure has a roof that fully covers the animal
113 |  |  | Give your animal a trunk |  |  | 400 | [12 empty] | The animal has a trunk
201 |  |  | Make a baby version of the animal |  |  | 500 | [12 empty] | There is a baby animal that is sufficiently similar to the parent
202 |  |  | Give your animal stripes |  |  | 600 | [12 empty] | The animal has stripes on 2 out of the body, legs and head
203 |  |  | Make a cart for the baby (or add a place for the baby on the transport) |  |  | 300 | [12 empty] | The baby has a means of transportation
204 |  |  | Make the animal at least 10cm high |  |  | 400 | [12 empty] | The animal is 10 cm high
205 |  |  | Make the animal at least 10cm long |  |  | 200 | [12 empty] | The animal is 10 cm long
206 |  |  | Give your animal tusks or fangs |  |  | 300 | [12 empty] | The animal has tushs or fangs
207 |  |  | Enlarge your enclosure to take the baby |  |  | 400 | [12 empty] | the baby and the parent fits within the enclosure
208 |  |  | Make the enclosure at least 10 cm by 10 cm |  |  | 400 | [12 empty] | The enclosure is at least 10cm by 10cm
209 |  |  | Give the animal 6 legs |  |  | 400 | [12 empty] | The animal has 6 legs
210 |  |  | Give your animal a second head |  |  | 200 | [12 empty] | The animal has at least 2 heads
211 |  |  | Give your animal a tail |  |  | 100 | [12 empty] | The animal has a tail
212 |  |  | Give your animal a mouth |  |  | 300 | [12 empty] | The animal has a mouth
301 |  |  | Put a gate on the enclosure to allow the animal egress |  |  | 200 | [12 empty] | There is a gate on the enclosure and the animal has egress
302 |  |  | Make the enclosure at least 4 blocks high |  |  | 200 | [12 empty] | The Enclosure is at least 4 thick blocks high all the way around
400 |  |  | Aesthetics |  |  | 2000 | [12 empty] | The animal, enclosure, and any transport vehicles look good and well constructed.

## Score2012-01
ID | Story | Value | Random | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6
1 | Build an animal | Must Have | bar: Team 1 to Team 4
2 | Make an enclosure for the animal | Must Have | bar: Team 1 to Team 4
101 | Give the animal four legs | 300 | 1.1898 | bar: Team 3 to Team 4
102 | Make an enclosure for the animal. Animal must have egress | 500 | 0.76618 | bar: Team 1 to Team 4
103 | Make a transport with wheels for your animal | 300 | 0.91555 | bar: Team 1 to Team 2; Team 4
104 | Give your animal wings | 300 | 1.8165 | bar: Team 2; Team 4
105 | Give your animal a head | 500 | 1.0621 | bar: Team 1 to Team 4
106 | Make sure your animal has at least two eyes | 300 | 0.2089 | bar: Team 1 to Team 4
107 | Make your animal one color | 200 | 0.68362 | bar: Team 2
108 | Make your animal freestanding on two legs | 200 | 0.41767
109 | Give your animal two arms | 200 | 1.552 | bar: Team 2 to Team 4
110 | Give your animal horns | 200 | 1.3268 | bar: Team 1; Team 4
111 | Give your animal antlers | 400 | 0.52482 | bar: Team 2 to Team 4
112 | Put a roof on the enclosure to cover the animal | 300 | 1.3428 | bar: Team 1 to Team 4
113 | Give your animal a trunk | 400 | 1.1981 | bar: Team 1 to Team 4
1
201 | Make a baby version of the animal | 500 | 1.3429 | bar: Team 1 to Team 3
202 | Give your animal stripes | 600 | 2.6186 | bar: Team 2 to Team 4
203 | Make a cart for the baby (or add a place for the baby on the transport) | 300 | 0.76989 | bar: Team 1 to Team 3
204 | Make the animal at least 10cm high | 400 | 1.1832 | bar: Team 1 to Team 4
205 | Make the animal at least 10cm long | 200 | 1.3116 | bar: Team 1 to Team 4
206 | Give your animal tusks or fangs | 300 | 0.9566 | bar: Team 1 to Team 2
207 | Enlarge your enclosure to take the baby | 400 | 0.9643 | bar: Team 1 to Team 3
208 | Make the enclosure at least 10 cm by 10 cm | 400 | 0.9293 | bar: Team 1 to Team 4
209 | Give the animal 6 legs | 400 | 0.83851 | bar: Team 1 to Team 3
210 | Give your animal a second head | 200 | 1.4857
211 | Give your animal a tail | 100 | 0.84872 | bar: Team 1 to Team 4
212 | Give your animal a mouth | 300 | 0.5907 | bar: Team 1 to Team 2; Team 4
1
301 | Put a gate on the enclosure to allow the animal egress | 200 | 0.56678 | bar: Team 1 to Team 3
302 | Make the enclosure at least 4 blocks high | 200 | 1.1337 | bar: Team 1 to Team 4
400 | Aesthetics | 2000 | 1.5722 | 0.5 | 1 | 1 | 0.5
|  |  | Base | 7200 | 9700 | 8600 | 6900 | 0 | 0
|  |  | Final | 7591.1032 | 11671.0366 | 10607.4543 | 8560.5885 | 0 | 0
|  |  | Rank | 4 | 1 | 2 | 3 | 5 | 5

## Score 2011-10
ID | Story | Value | Random | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6
1 | Build an animal | Must Have | 1 | bar: Team 1; Team 4
2 | Make an enclosure for the animal | Must Have | bar: Team 1; Team 4
101 | Give the animal four legs | 300 | 1 | bar: Team 4
102 | Make an enclosure for the animal. Animal must have egress | 500 | 1 | bar: Team 1; Team 4
103 | Make a transport with wheels for your animal | 300 | 1 | bar: Team 1; Team 4
104 | Give your animal wings | 300 | 1 | bar: Team 1; Team 4
105 | Give your animal a head | 500 | 1 | bar: Team 1; Team 4
106 | Make sure your animal has at least two eyes | 300 | 1 | bar: Team 1; Team 4
107 | Make your animal one color | 200 | 1
108 | Make your animal freestanding on two legs | 200 | 1 | bar: Team 1
109 | Give your animal two arms | 200 | 1 | bar: Team 1; Team 4
110 | Give your animal horns | 200 | 1 | bar: Team 1; Team 4
111 | Give your animal antlers | 400 | 1 | bar: Team 1; Team 4
112 | Put a roof on the enclosure to cover the animal | 300 | 1 | bar: Team 4
113 | Give your animal a trunk | 400 | 1 | bar: Team 1; Team 4
1
201 | Make a baby version of the animal | 500 | 1 | bar: Team 1; Team 4
202 | Give your animal stripes | 600 | 1 | bar: Team 1
203 | Make a cart for the baby (or add a place for the baby on the transport) | 300 | 1 | bar: Team 1; Team 4
204 | Make the animal at least 10cm high | 400 | 1 | bar: Team 1; Team 4
205 | Make the animal at least 10cm long | 200 | 1 | bar: Team 1; Team 4
206 | Give your animal tusks or fangs | 300 | 1 | bar: Team 1; Team 4
207 | Enlarge your enclosure to take the baby | 400 | 1 | bar: Team 1; Team 4
208 | Make the enclosure at least 10 cm by 10 cm | 400 | 1 | bar: Team 1; Team 4
209 | Give the animal 6 legs | 400 | 1 | bar: Team 1; Team 4
210 | Give your animal a second head | 200 | 1 | bar: Team 4
211 | Give your animal a tail | 100 | 1 | bar: Team 1; Team 4
212 | Give your animal a mouth | 300 | 1 | bar: Team 1
1
301 | Put a gate on the enclosure to allow the animal egress | 200 | 1 | bar: Team 4
302 | Make the enclosure at least 4 blocks high | 200 | 1 | bar: Team 1; Team 4
400 | Aesthetics | 2000 | 1 | Team 1: 1; Team 4: 0.7
|  |  | Base | 9400 | 0 | 0 | 8700 | 0 | 0
|  |  | Final | 9400 | 0 | 0 | 8700 | 0 | 0
|  |  | Rank | 1 | 3 | 3 | 2 | 3 | 3

## Score2011-05
ID | Story | Value | Random | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6
1 | Build an animal | Must Have
2 | Make an enclosure for the animal | Must Have
101 | Give the animal four legs | 300 | 0.75123
102 | Make an enclosure for the animal. Animal must have egress | 500 | 0.90785 | bar: Team 1 to Team 6
103 | Make a transport with wheels for your animal | 300 | 1.9212 | bar: Team 1 to Team 2; Team 4 to Team 6
104 | Give your animal wings | 300 | 1.6332 | bar: Team 1 to Team 3; Team 5 to Team 6
105 | Give your animal a head | 500 | 1.0264 | bar: Team 1 to Team 6
106 | Make sure your animal has at least two eyes | 300 | 0.69632 | bar: Team 1 to Team 6
107 | Make your animal one color | 200 | 0.46617 | bar: Team 1; Team 5
108 | Make your animal freestanding on two legs | 200 | 0.85843 | bar: Team 1 to Team 3; Team 6
109 | Give your animal two arms | 200 | 1.5834 | bar: Team 1 to Team 3; Team 5 to Team 6
110 | Give your animal horns | 200 | 1.2166 | bar: Team 1 to Team 6
111 | Give your animal antlers | 400 | 0.84966 | bar: Team 1 to Team 6
112 | Put a roof on the enclosure to cover the animal | 300 | 2.1904 | bar: Team 5 to Team 6
113 | Give your animal a trunk | 400 | 1.034 | bar: Team 1 to Team 6
201 | Make a baby version of the animal | 500 | 1.479 | bar: Team 1 to Team 6
202 | Give your animal stripes | 600 | 1.4398 | bar: Team 1 to Team 4; Team 6
203 | Make a cart for the baby (or add a place for the baby on the transport) | 300 | 1.3287 | bar: Team 1 to Team 3; Team 5 to Team 6
204 | Make the animal at least 10cm high | 400 | 0.91688 | bar: Team 1 to Team 6
205 | Make the animal at least 10cm long | 200 | 1.211 | bar: Team 1 to Team 6
206 | Give your animal tusks or fangs | 300 | 1.1357 | bar: Team 1 to Team 6
207 | Enlarge your enclosure to take the baby | 400 | 0.8094 | bar: Team 1 to Team 6
208 | Make the enclosure at least 10 cm by 10 cm | 400 | 0.91853 | bar: Team 1 to Team 6
209 | Give the animal 6 legs | 400 | 1.7255 | bar: Team 1 to Team 6
210 | Give your animal a second head | 200 | 0.80924 | bar: Team 1 to Team 3; Team 5 to Team 6
211 | Give your animal a tail | 100 | 1.6412 | bar: Team 1 to Team 6
212 | Give your animal a mouth | 300 | 0.93727 | bar: Team 1 to Team 6
301 | Put a gate on the enclosure to allow the animal egress | 200 | 0.92945 | bar: Team 1 to Team 6
302 | Make the enclosure at least 4 blocks high | 200 | 1.3563 | bar: Team 1 to Team 6
400 | Aesthetics | 2000 | 0.55157 | 1 | 0.6 | 0.6 | 0.6 | 1 | 0.6
|  |  | Base | 9600 | 9000 | 8700 | 7800 | 9500 | 9300
|  |  | Final | 9631.024 | 9786.744 | 9210.3738 | 8247.9589 | 9942.802 | 10443.8711
|  |  | Rank | 4 | 3 | 5 | 6 | 2 | 1

## Print
ID | Story | Iter1 | Iter2 | Iter3 | Iter4 | Value Points | Severity | Priority | Fix Target | Reported By | Assigned To | Date Reported | PEF | Fixed On | Closed On | Fixed Build/cycle | Fixed Version | Additional Info | Test
1 | Build an animal |  |  |  |  | Must Have | [12 empty] | It looks like an animal
2 | Make an enclosure for the animal |  |  |  |  | Must Have | [12 empty] | The animal fits in the enclosre and has egress
101 | Give the animal four legs |  |  |  |  | 300 | [12 empty] | The animal has exactly 4 legs
102 | Make an enclosure for the animal. Animal must have egress |  |  |  |  | 500 | [12 empty] | The animal fits in the enclosre and has egress
103 | Make a transport with wheels for your animal |  |  |  |  | 300 | [12 empty] | The animal (all supporting legs) fit on the transport
104 | Give your animal wings |  |  |  |  | 300 | [12 empty] | The animal has wings
105 | Give your animal a head |  |  |  |  | 500 | [12 empty] | The animal has a head
106 | Make sure your animal has at least two eyes |  |  |  |  | 300 | [12 empty] | the animal has at least 2 eyes
107 | Make your animal one color |  |  |  |  | 200 | [12 empty] | The animal body, head,and legs are made of one color
108 | Make your animal freestanding on two legs |  |  |  |  | 200 | [12 empty] | The animal can freely stand on 2 legs.
109 | Give your animal two arms |  |  |  |  | 200 | [12 empty] | The animal has 2 arms
110 | Give your animal horns |  |  |  |  | 200 | [12 empty] | The animal has horns
111 | Give your animal antlers |  |  |  |  | 400 | [12 empty] | The animal has antlers
112 | Put a roof on the enclosure to cover the animal |  |  |  |  | 300 | [12 empty] | The enclosure has a roof that fully covers the animal
113 | Give your animal a trunk |  |  |  |  | 400 | [12 empty] | The animal has a trunk
201 | Make a baby version of the animal |  |  |  |  | 500 | [12 empty] | There is a baby animal that is sufficiently similar to the parent
202 | Give your animal stripes |  |  |  |  | 600 | [12 empty] | The animal has stripes on 2 out of the body, legs and head
203 | Make a cart for the baby (or add a place for the baby on the transport) |  |  |  |  | 300 | [12 empty] | The baby has a means of transportation
204 | Make the animal at least 10cm high |  |  |  |  | 400 | [12 empty] | The animal is 10 cm high
205 | Make the animal at least 10cm long |  |  |  |  | 200 | [12 empty] | The animal is 10 cm long
206 | Give your animal tusks or fangs |  |  |  |  | 300 | [12 empty] | The animal has tusks or fangs
207 | Enlarge your enclosure to take the baby |  |  |  |  | 400 | [12 empty] | the baby and the parent fits within the enclosure
208 | Make the enclosure at least 10 cm by 10 cm |  |  |  |  | 400 | [12 empty] | The enclosure is at least 10cm by 10cm
209 | Give the animal 6 legs |  |  |  |  | 400 | [12 empty] | The animal has 6 legs
210 | Give your animal a second head |  |  |  |  | 200 | [12 empty] | The animal has at least 2 heads
211 | Give your animal a tail |  |  |  |  | 100 | [12 empty] | The animal has a tail
212 | Give your animal a mouth |  |  |  |  | 300 | [12 empty] | The animal has a mouth
301 | Put a gate on the enclosure to allow the animal egress |  |  |  |  | 200 | [12 empty] | There is a gate on the enclosure and the animal has egress
302 | Make the enclosure at least 4 blocks high |  |  |  |  | 200 | [12 empty] | The Enclosure is at least 4 thick blocks high all the way around
400 | Aesthetics |  |  |  |  | 2000 | [12 empty] | The animal, enclosure, and any transport vehicles look good and well constructed.