## Slide 1: Risky Business: Real Options for Software Development
Todd Little
VP Product Development, IHS
Notes: Todd comes from Oil and Gas exploration, a business that deals with risk in many facets. Chris comes from investment banking, another area that has made it important to understand and comprehend issues associated with risk. Both Todd and Chris have spent their careers developing software in these industries.

## Slide 2: Risk and Uncertainty
 | Risk | Uncertainty
Frank Knight | Immeasurable | Quantifiable
PMI | Risk can be positive or negative | ???
English | A situation involving exposure to danger | The state of being uncertain Not known or established; questionable

## Slide 3: Risky Business

## Slide 4: Hurricane Rita
Notes: What can we say about every one of these predictions? They are wrong. But the collective set of predictions is quite useful. Which is more important when predicting hurricanes – where it hits or when it hits? Ok, both are important, but where is much more important than when. If you are in Florida you don’t really care when it hits. But once you know it has a chance to hit Houston then it is very important to know when it might hit.

## Slide 5: The Cone of Uncertainty
We expect uncertainty and manage for it through iterations, anticipation, and adaptation.
Notes: Inspection and adaptation is the answer. Iterations help bring in new information

## Slide 6: War
They couldn't hit an elephant at this dist…
Last words of General John B. Sedgwick, Union Army Civil War officer, uttered during the Battle of Spotsylvania, 1864
Notes: War – now that’s an area with lots of risk. I guess he didn’t do too well in his prediction.

## Slide 7: Gordon the Guided Missile

## Slide 8: Movies
78% of Films Lose Money
6% of films make 80% of profit
Notes: Most movies strive to be the next Titanic, the largest grossing film of all time.
The reality is that the vast majority really do end up closer to the real Titanic than to the movie Titanic.

## Slide 9: Books
300,000 in 2004,
<25% sold more
Than 100 copies
Notes: Books. Here is my book. Doesn’t it look like it is chock full of useful stuff?
But only 25% of books sell more than 100 copies. Please do your part so that I am not part of that statistic.

## Slide 10: Poker

## Slide 11: Texas Hold’em: Which is the best hole hand?
A
B
C

## Slide 12: Texas Hold’em: Which is the best hole hand?
33.5%
29.6%
36.5%
A
B
C

## Slide 13: Poker Metric: Percent of Hands Won

## Slide 14: Oil & Gas Exploration
Notes: Oil exploration is highly risky. It used to be that 10% was a good find rate for wildcat wells. Based on improvements in technology this is closer to 20%. Still risky, but that risk is acceptable because the payout is enormous. The key is having a diversified portfolio to balance the risk exposure.

## Slide 15: Oil & Gas Exploration
90-80% Failure
Notes: Oil exploration is highly risky. It used to be that 10% was a good find rate for wildcat wells. Based on improvements in technology this is closer to 20%. Still risky, but that risk is acceptable because the payout is enormous. The key is having a diversified portfolio to balance the risk exposure.

## Slide 16
I’m beginning to think it wasn’t such a good idea to turn off those unit tests
Notes:   Safety is not to be messed with.
  Test, Test, Test
  Test again with real data
  Test, Test, Test
  Test again with real data

## Slide 17: Which Uncertainties Are Important?
Notes: Oil and gas geologists and engineers build models to help them comprehend the uncertainties. This is a tornado chart, because it looks like a tornado. This chart clearly shows that the largest uncertainty is associated with Reserves, with the next largest uncertainty being oil/gas price. This gives the engineer something to focus on. Perhaps there is additional data that can be collected to help reduce the uncertainty bars. There may not be anything that can be done about Oil/gas price. Perhaps futures contracts could be used to hedge some of the uncertainty. The other uncertainties may not be worth spending too much time since they have limited effect on the total uncertainty.

## Slide 18: Risk management tools

## Slide 19: Real Options
The right — but not the obligation — to undertake certain actions prior to an expiry date

## Slide 20: Airline Tickets
The right — but not the obligation — to undertake certain actions prior to an expiry date

## Slide 21: Real Options
The right, but not the obligation to take some action prior to an expiry date

## Slide 22: Do you have a choice?
Option
Commitment
Decision

## Slide 23
Notes: http://www.flickr.com/photos/nick_anderson/5049751331/sizes/m/in/photostream/

## Slide 24
Value of Information
Value of Flexibility
Cost of Delay
Value of Uncertainty

## Slide 25: Value of Uncertainty
What is the source of all value?

## Slide 26: Value of Uncertainty
Efficient Frontier

## Slide 27: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  | ██ | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  | █ | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 28: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  |  | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 29: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ |  |  |  |  | 
Schedule Uncertainty |  |  |  | ███ | ██ |  |  |  |  | 
General Market Uncertainty |  |  |  | ██ | ██ |  |  |  |  | 
Cost Uncertainty |  |  |  | ██ | █ |  |  |  |  | 

## Slide 30: Value of Information

## Slide 31: Value of Information

## Slide 32: Value of Information

## Slide 33: Value of Information

## Slide 34: Increasing Value & Cost of Info.
Value or Cost
Value of Information
Cost
$0
$$$
Low certainty
High certainty
EVPI
Aim for this range
Perfect Information

## Slide 35: Software Development
Examples of Value of Information

## Slide 36: POC can increase risk
POC is intended to show if something is possible
With software almost anything is possible
Therefore, the answer to almost every POC is YES
At that point expectations are set high
What risk is actually reduced?
Instead design POC to expose the biggest risks that we need to understand

## Slide 37: Value of Flexibility
Notes: 9 research projects for drive train
1 chassis – same hole for all 9 drive trains
VOI from 9 research projects, VOF from chassis design
Contrast this with the development of the Prius. Toyota had 9 different research projects running to develop hybrid engine technologies. Normally they would choose a drivetrain first, and build a car around it. Instead Toyota decided to keep its options open, and designed the Prius with a hole in it for the drive train. The 9 research projects continued, and 9+ months after the Prius development project was started, a drive train was chosen. Toyota knew that this car needed a radically new drive train architecture. Instead of guessing and choosing one, they let all 9 research projects continue their work, and as they did, the best option for the car's engine became clear. So was 9 research projects a waste? No because each project was generating factual information about the options for hybrid engine design, information that Toyota engineering management needed to make an informed choice.

## Slide 38: Software Development
Value of Flexibility from Loose Coupling

## Slide 40: Cost of Delay
Value Loss from Delay

## Slide 41: Wrong Priorities
Notes: The first generation of Ford Taurus turned out to be the best selling car in America in the
late 1980s. Conceived in the 1980's and introduced in 1986, it set the standard for new practices
in project management and product development. It was one of the early projects in the U.S.,
which fully utilized the concept of cross-functional teams and concurrent engineering practices.
It established close ties with vendors and subcontractors, and was characterized by a spirit of
cooperation and strong synergy among teams. The result was a remarkable market and business
success. Its revolutionary design and outstanding quality, created a new trend in the U.S.
automobile industry, and customers simply loved the car. Yet, when the project was completed,
the project manager was fired. His “sin” was that project completion was delayed by six months.
In contrast, the second generation of Ford Taurus was developed in the early 1990s and
2
completed in 1995. With increased competition and the enormous success of Japanese imports,
Ford had hoped to reestablish Taurus, once again, as the best selling car in America. But the new
project manager learned the lesson of his predecessor: He considered project schedule as a “holy
grail,” and made sticking to the completion date the ultimate goal, while sacrificing other things.
Vendor relationships, team spirit, and product integration were just few of the issues that
suffered. The second generation of Taurus turned out to be a disappointing business experience.
It did not recapture the position of the best selling car in America and Ford was not able to repeat
its outstanding success of the first Taurus.

## Slide 42: Risk Management is not Risk Aversion

## Slide 43: Contact
Todd Little
  todd.little@ihs.com
  toddelittle@gmail.com
  www.linkedin.com/in/ toddelittle/
  www.toddlittleweb.com
  www.accelinnova.com

## Slide 44: Real Options
Value of Information
Value of Flexibility

## Slide 48: Delivery Failure results in Collateral Damage
Notes: When the Denver Airport baggage handling system was designed, for example, no one asked what would happen if the fully automated system failed. How would baggage be handed? No one thought about it and there we no accommodations made in the airport plan. So when the system did fail there were no other alternatives to move baggage around the airport. There were no underground roadways on which to manually move luggage using tugs.

## Slide 49: Risk Management and Real Options
Traditional Baggage
Automated Baggage
Airport

## Slide 50: Making An Agile Conference Agile
Chart: Submissions for 2011 compared to 2010
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Y2010 | 916 | 899 | 810 | 629 | 547 | 496 | 453 | 412 | 387 | 367 | 327 | 301 | 278 | 260 | 237 | 227 | 219 | 210 | 197 | 190 | 177 | 163 | 151 | 144 | 131 | 120 | 115 | 106 | 93 | 89 | 84 | 82 | 80 | 73 | 68 | 62 | 57 | 53 | 50 | 46 | 40 | 33 | 32 | 30 | 26 | 23 | 18 | 10 | 1
Y2011-IT1 | 473 | 282 | 171 | 146 | 116 | 96 | 72 | 63 | 49 | 46 | 42 | 40 | 38 | 31 | 23 | 17 | 13 | 0 | 9 | 9 | 7 | 7 | 5 | 0 | 4 | 1
Y2011-IT2 | 938 | 785 | 732 | 714 | 687 | 672 | 657 | 647 | 612 | 604 | 599 | 593 | 588 | 572 | 571 | 561 | 556 | 555 | 551 | 546 | 544 | 538 | 534 | 531 | 529 | 523 | 522 | 516 | 510 | 505 | 504 | 502 | 495 | 492 | 488
5 Extra weeks to review sessions

## Slide 51
Chart: Estimated Agile 2010 Attendance
| 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | FINAL
Most Likely | 1400 | 1364.5243 | 1120.1596 | 971.8365 | 1047.0469 | 1111.6133 | 1255.6124 | 1241.4581 | 1280.5708 | 1251.8608 | 1272.45 | 1295.6802 | 1330.7759 | 1396.1783 | 1430.0961 | 1418.2858 | 1336
Pessimistic | 1200 | 1178.5951 | 939.7996 | 797.7668 | 889.4518 | 969.3672 | 1129.9984 | 1128.1304 | 1180.5262 | 1163.8541 | 1197.2486 | 1233.2142 | 1281.0642 | 1359.338 | 1405.7486 | 1406.1182 | 1336
Optimistic | 1700 | 1643.418 | 1390.6995 | 1232.9411 | 1283.4394 | 1324.9825 | 1444.0333 | 1411.4497 | 1430.6377 | 1383.8708 | 1385.252 | 1389.3793 | 1405.3435 | 1451.4388 | 1466.6173 | 1436.5372 | 1336

## Slide 52: Uncertainty Bounds
Chart: Cumulative Distribution Function of Actual/Estimate Ratio
| 0.62314540059347479 | 0.63489950752030033 | 0.759457933370978 | 0.8652514997692663 | 1.033623910336239 | 1.1229946524064141 | 1.1518915866741932 | 1.4538093485461876 | 1.8247220405493778 | 1.8933428775948462 | 1.9447219447219461 | 2.0391608391608367 | 2.0808080808080787 | 2.6543209876543212 | 2.7804642166344355 | 2.8652037617554882 | 3.0856643356643354 | 3.4029484029483981 | 3.8833992094861682 | 4.9197860962566864
DeMarco Data | 0.025 | 0.075 | 0.125 | 0.175 | 0.225 | 0.275 | 0.325 | 0.375 | 0.425 | 0.475 | 0.525 | 0.575 | 0.625 | 0.675 | 0.725 | 0.775 | 0.825 | 0.875 | 0.925 | 0.975
DeMarco Log-Normal | 0.047419 | 0.05051 | 0.088876 | 0.12819 | 0.19908 | 0.23896 | 0.252 | 0.38649 | 0.53276 | 0.55663 | 0.57382 | 0.6039 | 0.61656 | 0.75602 | 0.77914 | 0.7934 | 0.82618 | 0.86408 | 0.90562 | 0.95545
10-20% on time
10% exceed 3-4x
Median project 1.7x

## Slide 53: The A/B/C List sets proper expectations
A | MUST be completed in order to ship the product and the schedule will be slipped if necessary to make this commitment.
B | Is TARGETED to be completed in order to ship the product, but may be dropped without consequence.
C | Is NOT TARGETED to be completed prior to shipping, but might make it if time allows.
Only “A” features may be committed to customers.
If more than 50% of the planned effort is allocated to “A” items the project is at risk.

## Slide 54: A/B/C List
A
50%
100%
Backlog Plan
Typical Delivery
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date

## Slide 55: A/B/C List
50%
100%
Backlog Plan
Uncertainty Risk
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date
A
Notes: Need some explanation to go along with this slide and the previous one.
--The idea is that there is uncertainty in the estimation process. A factor of 2X is a generally sufficient buffer if the team has gotten basic estimation down. Thus is it possible that what is actually delivered is only the “A” items. That is ok and actually expected.

## Slide 57: Estimating Story Difficulty
Estimation |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value