## Slide 1: The Value Uncertainty Game
Todd Little
VP Product Development
IHS

## Slide 2: Estimation Exercise

## Slide 3: Simulation Exercise
ID: 1 Value: Sum of all dice
Major feature
Test: Roll 3 dice - 2 or more dice are the same

## Slide 4: ABC’s of Prioritization

## Slide 5: The A/B/C List sets proper expectations
A | MUST be completed in order to ship the product and the schedule will be slipped if necessary to make this commitment.
B | Is WISHED to be completed in order to ship the product, but may be dropped without consequence.
C | Is NOT TARGETED to be completed prior to shipping, but might make it if time allows.
Only “A” features may be committed to customers.
If more than 50% of the planned effort is allocated to “A” items the project is at risk.

## Slide 6: A/B/C List
A
50%
100%
Backlog Plan
Typical Delivery
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date

## Slide 7: A/B/C List
50%
100%
Backlog Plan
Uncertainty Risk
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date
A
Notes: Need some explanation to go along with this slide and the previous one.
--The idea is that there is uncertainty in the estimation process. A factor of 2X is a generally sufficient buffer if the team has gotten basic estimation down. Thus is it possible that what is actually delivered is only the “A” items. That is ok and actually expected.

## Slide 8
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
Priority

## Slide 9: Simulation Exercise
ID: 1 Value: Sum of all dice
Major feature
Test: Roll 3 dice - 2 or more dice are the same

## Slide 10: Example Story
ID: 1 Value: Sum of all dice
Major feature
Test: Roll 3 dice - 2 or more dice are the same
Fail
Value = 3+1+3 = 7

## Slide 11: Stories and Scoring
Points are scored for accepted stories.
Value is just an estimate…the market will decide
We will run 3 iterations, with 10 rolls of the dice per iteration
WIP limit of one story in progress
Must commit to 6 stories for the release, and 2 stories per iteration
ID: 1 Value: Sum of all dice
Major feature
Test: Roll 3 dice - 2 or more dice are the same

## Slide 12: Release Planning (5 minutes)
Estimate how much time each story will take, S, M, L, or XL
Estimate how much value each story will have. Map onto the value/cost chart
Prioritize and commit at least 6 stories. Get 10 commit points per story committed and delivered. Miss any commitment and you will get 0 points.
  Mark committed stories with an “A” Mark remaining stories with a “B” or “C”

## Slide 13
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
Priority

## Slide 14: 3 Iterations
Estimation updates
  Estimate any new stories
  Tweak any of the prior estimates if desired
Story signup
  Commit to at least 2 stories by pulling them into the Iteration Backlog
  You get 5 points per committed story delivered. If you miss any commitment you get 0 commit points for that iteration. If you deliver a story that is not committed you get 0 commit points for that story

## Slide 15: Special Actions
It is ok abandon a story
  You can come back to it later
It is ok to redo a story
  Pull it back into the backlog
  Work it just as before to pass the test
  If the new development is not better than the previous result, then revert to the previous result.

## Slide 16
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
Priority

## Slide 17: The Progress Board
Backlog | Committed | In Work | Accepted
Committed for this release (A) Cutline Potential stories | Committed for this iteration | In Development | Passes test criteria

## Slide 18: Keeping Score
Iter | Day | Story# | Red | Green | White | Blue | Value Pts | Iter Commit | Rel Commit
1 | 1 |  |  |  |  |  |  |  | 
1 | 2 | 4 | 4 | 5 | 3 | 4 | 60 |  | 
1 | 3 |  |  |  |  |  |  |  | 
1 | 4 | 1 | 4 | 5 | 3 | 4 |  |  | 
1 | 5 | 1 | 3 | 1 | 3 | 4 | 7 |  | 
1 | 6 |  |  |  |  |  |  |  | 
1 | 7 |  |  |  |  |  |  |  | 
1 | 8 |  |  |  |  |  |  |  | 
1 | 9 |  |  |  |  |  |  |  | 
1 | 10 |  |  |  |  |  |  |  | 
1 | Total |  |  |  |  |  |  |  | 
2 | 1 |  |  |  |  |  |  |  | 
2 | 2 |  |  |  |  |  |  |  | 
2 | 3 |  |  |  |  |  |  |  | 
2 | 4 |  |  |  |  |  |  |  | 
2 | 5 |  |  |  |  |  |  |  | 
2 | 6 |  |  |  |  |  |  |  | 
2 | 7 |  |  |  |  |  |  |  | 
2 | 8 |  |  |  |  |  |  |  | 
2 | 9 |  |  |  |  |  |  |  | 
2 | 10 |  |  |  |  |  |  |  | 
2 | Total |  |  |  |  |  |  |  | 

## Slide 19: Keeping Score
ID | Category | Value | Test | Priority (A/B/C) | Value | Rel Commit | Iter Commit | Rel Com Pts | It Com Pts | Cost
1 | Major feature | Sum of all dice | Roll 3 dice - 2 or more dice are the same | A |  | X | 1 |  |  | 
2 | Major feature | Sum of matching dice | Roll 4 dice - 2 or more dice are the same | B |  |  |  |  |  | 
3 | Research | product of dice | Roll 2 dice - 2 or more dice are the same | C |  |  |  |  |  | 
4 | Major Research | product of dice | Roll 3 dice - Three consecutive integers (straight) | A |  | X | 2 |  |  | 
5 | Moderate enhancement | Sum of all (3) dice | Roll 3 dice - No 1s |  |  |  |  |  |  | 
6 | Moderate enhancement | Sum of all (3) dice | Roll 3 dice - No 6s |  |  |  |  |  |  | 
7 | Enhancement | Sum of all (2) dice | Roll 2 dice - No 1s |  |  |  |  |  |  | 
8 | Enhancement | Sum of all (2) dice | Roll 2 dice - No 6s |  |  |  |  |  |  | 
9 | Incremental feature | Sum of all (1) dice | Roll 1 die - No 1s |  |  |  |  |  |  | 
10 | Incremental feature | Sum of all (1) dice | Roll 1 die - No 6s |  |  |  |  |  |  | 
 | Total |  |  |  |  |  |  |  |  |