## Slide 1: Mythbusting Software Estimation
Todd Little
VP Product Development
IHS
Notes: Todd comes from Oil and Gas exploration, a business that deals with risk in many facets. Chris comes from investment banking, another area that has made it important to understand and comprehend issues associated with risk. Both Todd and Chris have spent their careers developing software in these industries.

## Slide 2
Test First

## Slide 3
#1: Estimation challenges are well understood by General Management, Project Management, and Teams and it is normal to be able to estimate projects within 25% accuracy.

## Slide 4
#2: Estimation accuracy significantly improves as the project progresses

## Slide 5
#3: Estimations are frequently impacted by biases and these biases can be significant.

## Slide 6
#4: We’re pretty good at estimating things relatively

## Slide 7
#5: Velocity/Throughput is a good tool for adjusting estimates.

## Slide 8
#6: We’re a bit behind, but we’ll make it up in testing since most of our uncertainty was in the features.

## Slide 9
#7: Scope Creep is a major source of estimation error.

## Slide 10
#8: Having more estimators, even if they are not experts, improves estimation accuracy

## Slide 11
#9: Project success is determined by on-time delivery

## Slide 12
#10: Estimation is waste

## Slide 13
#1: Estimation challenges are well understood by General Management, Project Management, and Teams and it is normal to be able to estimate projects within 25% accuracy.

## Slide 14: Managing the Coming Storm Inside the Cyclone
When will we get the requirements?
All in good time, my little pretty, all in good time
But I guess it doesn't matter anyway
Doesn't anybody believe me?
You're a very bad man!
Just give me your estimates by this afternoon
No, we need something today!
I already promised the customer it will be out in 6 months
No, we need it sooner.
Not so fast! Not so fast! ... I'll have to give the matter a little thought. Go away and come back tomorrow
Ok then, it will take 2 years.
Team Unity
Project Kickoff
Notes: We look at a typical software project…..

## Slide 15: We’re not in Kansas Anymore
My! People come and go so quickly here!
I may not come out alive, but I'm goin' in there!
The Great and Powerful Oz has got matters well in hand.
"Hee hee hee ha ha! Going so soon? I wouldn't hear of it! Why, my little party's just beginning!
Developer Hero
Reorg
Testing

## Slide 16: Why is Software Late? Genuchten 1991 IEEE
General Manager | Project Manager | Item
1 | 10 | Insufficient front end planning
2 | 3 | Unrealistic project plan
3 | 8 | Project scope underestimated
4 | 1 | Customer/management changes
5 | 14 | Insufficient contingency planning
6 | 13 | Inability to track progress
7 | 5 | Inability to track problems early
8 | 9 | Insufficient Number of checkpoints
9 | 4 | Staffing problems
10 | 2 | Technical complexity
11 | 6 | Priority Shifts
12 | 11 | No commitment by personnel to plan
13 | 12 | Uncooperative support groups
14 | 7 | Sinking team spirit
15 | 15 | Unqualified project personnel

## Slide 17: The Context of Feedback

## Slide 18: Why is Software Late? Genuchten 1991 IEEE
General Manager | Project Manager | Item
H | H | Customer/management changes
H | H | Unrealistic project plan
M | H | Staffing problems
L | H | Overall complexity
H | L | Insufficient front end planning
Notes: The project manager is much closer to the actual work being done and so I tend to think their response is closer to reality. What is of particular interest is where there is a discrepancy between the General Manager and the Project Manager.
1 4 Customer/management changes
PM: They were constantly changing their minds GM:OK, so we changed a few things once in a while
2 10 Technical complexity
PM: We were using new technology and had to discover all the limitations GM: I just to them to make it look like that cool demo I saw
3 2 Unrealistic project plan
PM: We told them it would take longer GM: I had to push them so that they would be serious
4 9 Staffing problems
PM: We couldn’t get the people we needed GM: I gave them everyone I had available
5 7 Inability to track problems early
PM/GM: agree --- We didn’t know what we didn’t know
6 11 Priority Shifts
PM: They were constantly changing their minds GM: We didn’t change that much
7 14 Sinking team spirit
PM: The team felt overworked and underappreciated GM: We’ve got a great team. What spirit they have
8 3 Project scope underestimated
PM: I didn’t really feel that we underestimated it. We told them it would be hard GM: We really didn’t think it was such a big project
9 8 Insufficient Number of checkpoints
PM/GM agree – it would have been good to have better visibility into what was going on
10 1 Insufficient front end planning
PM: We had a plan, but they didn’t like the answer and kept changing their mind GM: It all would have been fine if we could have just planned better
11 12 No commitment by personnel to plan
PM/GM agree – team was willing to commit
12 13 Uncooperative support groups
PM/GM agree – support groups were willing to help
13 6 Inability to track progress
PM: We had pretty good tracking GM: I wish I had better visibility into what was going on so I could have done something
14 5 Insufficient contingency planning
PM: We had decent contingency planning, we just weren’t able to do anything GM: We just needed better planning
15 15 Unqualified project personnel
PM/GM agree – people are our most important assets

## Slide 19: Negotiation Bias
"It is difficult to get a man to understand something when his salary depends upon his not understanding it.“
        Upton Sinclair:

## Slide 20: Space Shuttle Challenger
 | Engineers | Management
Probability of loss of life | 1 in 100 | 1 in 100,000
135 Flights
2 Disasters
14 Deaths

## Slide 21: IEEE Software, May/June 2006
Notes: This is from an IEEE Software article that I published in May 2006

## Slide 22: Accuracy of Initial Estimate
Chart: Initial Estimate vs. Actual Duration
| 0 | 1000
Ideal | 0 | 1000
DeMarco | 231 | 477 | 269 | 750 | 249 | 147 | 204 | 395 | 837 | 529 | 584 | 729 | 824 | 946 | 575 | 457 | 353 | 277 | 786 | 184

## Slide 23: Data From Steve McConnell

## Slide 24: Uncertainty
Percentage of Projects | 
10-20% | Less than or equal to original estimate
50% | Less than 2X original estimate
80-90% | Less than 4X original estimate

## Slide 25: Actual vs. Original Estimate
Chart: 
| 10-20% | 50% | 80-90%
Series 1 | 1 | 2 | 4

## Slide 26: 5
John Helm
Agile 2013

## Slide 27: Jørgensen 2013
Put software development project for bid on online marketplace vWorker.com
Received 16 bids.
Reduced down to 6 bids from vendors that had high (9.5) client satisfaction.
All 6 bidders went ahead and built the software

## Slide 28: Jørgensen 2013
Highest Estimate 8x the Lowest
Actual/Estimate Range: 0.7 – 2.9 (4x)
Actual Performance Range: Worst took 18X the effort of the best
Chart: 
| Estimate | Ratio of Actual to Estimate | Actual
Best | 1 | 0.7 | 1
Worst | 8 | 2.9 | 18

## Slide 29
#1: Estimation challenges are well understood by General Management, Project Management, and Teams and it is normal to be able to estimate projects within 25% accuracy.

## Slide 30
#2: Estimation accuracy significantly improves as the project progresses

## Slide 31: How does Estimation Accuracy Improve Over Time?
Chart: Cone of Uncertainty from Boehm
| Feasibility | Concept of Operation | Requirements Spec | Product Design Spec | Detail Design Spec | Accepted Software
 | -0.60206 | -0.30103 | -0.17609 | -0.09691 | -0.041393 | 0
 | 0.60206 | 0.30103 | 0.17609 | 0.09691 | 0.041393 | 0
4x
Notes: The conventional wisdom is that estimation gets better as the project progresses. This was first stated by Barry Boehm in COCOMO II, and stated by many authors subsequently, most notably Steve McConnell. At the Feasibility state the uncertainty band is 16X, while at Concept it has narrowed to 4X and by the Requirements it has reduced to 2.25X. This makes a lot of sense.

## Slide 32: Landmark Cone of Uncertainty
Chart: Estimation Error over Time

## Slide 33: But is Uncertainty Really Reduced?
“Take away an ordinary person’s illusions and you take away happiness at the same time.”
Henrik Ibsen--Villanden

## Slide 34: The Real Business Question
How much work do we have left to do and when will we ship?

## Slide 35: Remaining Uncertainty
4x

## Slide 36: Remaining Uncertainty
Story Estimate

## Slide 37
#2: Estimation accuracy significantly improves as the project progresses

## Slide 38
#3: Estimations are frequently impacted by biases and these biases can be significant.

## Slide 39: Optimism Bias
Chart: Estimation Error over Time

## Slide 40: Test 1 (Jørgensen IEEE Software 2008)
Group | Guidance | Result
A | 800 | 
B | 40 | 
C | 4 | 
D | None | 160

## Slide 41: Test 1
Group | Guidance | Result
A | 800 | 300
B | 40 | 100
C | 4 | 60
D | None | 160

## Slide 42: Test 2
Group | Guidance | Result
A | Minor Extension | 
B | New Functionality | 
C | Extension | 50

## Slide 43: Test 2
Group | Guidance | Result
A | Minor Extension | 40
B | New Functionality | 80
C | Extension | 50

## Slide 44: Test 3
Group | Guidance | Result
A | Future work at stake, efficiency will be measured | 
B | Control | 100

## Slide 45: Test 3
Group | Guidance | Result
A | Future work at stake, efficiency will be measured | 40
B | Control | 100

## Slide 46: Understand Bias
"What gets us into trouble is not what we don't know. It's what we know for sure that just ain't so.“
        Mark Twain

## Slide 47
#3: Estimations are frequently impacted by biases and these biases can be significant.

## Slide 48
#4: We’re pretty good at estimating things relatively

## Slide 49: Anchoring

## Slide 50: Relative Anchoring
“A” relative to “B” is not symmetric with “B” relative to “A”
Jørgensen IEEE Software March 2013
  Austria’s population is 70% of Hungary’s (Austria relative to Hungary), while Hungary’s population is 80% of Austria’s (Hungary relative to Austria).

## Slide 51: Relative Estimation Studies?
An evaluation of the paired comparisons method for
software sizing
Eduardo Miranda

## Slide 52: Relative Sizing - Dimensionality
Low by 4X

## Slide 53
#4: We’re pretty good at estimating things relatively

## Slide 54
#5: Velocity/Throughput is a good tool for adjusting estimates.

## Slide 55
Velocity
Scope Creep
Burnup Chart

## Slide 56: Velocity Helps Remove Bias
Chart: 
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Projected Ship Date | 40086 | 40433.1 | 40207.6696 | 40138.0244 | 40087.44 | 40140.6185 | 40120.7566 | 40120.7566

## Slide 57: But Velocity is not a Silver Bullet
Story Estimate

## Slide 58
#5: Velocity is a good tool for adjusting estimates.

## Slide 59
#6: We’re a bit behind, but we’ll make it up in testing since most of our uncertainty was in the features.

## Slide 60: Lan Cao - Estimating Agile Software Project Effort: An Empirical Study
2X
Uncertainty
Notes: Lessons learned: If uncertainty is high, work on it earlier. Reduce Technical Debt—Get to potentially shippable at each iteration. Finding and fixing the last bugs has high uncertainty – plan on there being uncertainty.

## Slide 61
#6: We’re a bit behind, but we’ll make it up in testing since most of our uncertainty was in the features.

## Slide 62
#7: Scope Creep is a major source of estimation error.

## Slide 63: We want this
Efficiency
Predictability
Social Networking
Agile
Late projects
Integration
Revenue
BPM
SOA
Mobility
CLOUD
Innovation
Business
Intelligence
Notes: Chris taped one of the investment bankers at his previous job

## Slide 64: Scope Creep
Capers Jones
  2% per month
  27% per year
Velocity
Scope Creep

## Slide 65: Estimate Velocity Net of Scope Creep
Chart: Impact of 2%/month Scope Creep
| 2 | 10 | 20 | 30 | 40 | 50
Ratio | 1.0417 | 1.25 | 1.6667 | 2.5 | 5

## Slide 66
Success vs. Project Duration -- Larman / Standish

## Slide 67
#7: Scope Creep is a major source of estimation error.

## Slide 68
#8: Having more estimators, even if they are not experts, improves estimation accuracy

## Slide 69: Group Estimation Exercise
Number of Jellybeans in the jar

## Slide 70: Actual vs. Original Estimate Range (p90/p10)
Chart: 
| Individuals | Groups | Ave of Individuals
Series 1 | 6 | 2 | 1.5

## Slide 71: Wisdom of Crowds
Jelly Beans
“Who Wants To Be a Millionaire?” audience correct 91%
Dutch Tulip Mania 1637

## Slide 72: Ask the Team
Chart: 
| 40602 | 40607 | 40609 | 40612 | 40612 | 40617 | 40617 | 40618 | 40634 | 40648 | 40664 | 40664 | 40724
 | 0.038462 | 0.11538 | 0.19231 | 0.26923 | 0.34615 | 0.42308 | 0.5 | 0.57692 | 0.65385 | 0.73077 | 0.80769 | 0.88462 | 0.96154

## Slide 73
#8: Having more estimators, even if they are not experts, improves estimation accuracy

## Slide 74
#9: Project success is determined by on-time delivery

## Slide 75: Delivery Challenges/Failures
Standish Group 2006, reported by CEO Jim Johnson, CIO.com, ‘How to Spot a Failing Project’
Notes: Delivery failures are well documented in the software business.
This is the classic report from Standish showing only 35% of projects delivered on time with expected features. 46% were challenged and 19% were killed. This is from 2006, and is a substantial improvement from the 19% success rate in 1996.

## Slide 76
Why do we care about on-time delivery?

## Slide 77: Cost of Delay

## Slide 78: Wrong Priorities
Notes: The first generation of Ford Taurus turned out to be the best selling car in America in the
late 1980s. Conceived in the 1980's and introduced in 1986, it set the standard for new practices
in project management and product development. It was one of the early projects in the U.S.,
which fully utilized the concept of cross-functional teams and concurrent engineering practices.
It established close ties with vendors and subcontractors, and was characterized by a spirit of
cooperation and strong synergy among teams. The result was a remarkable market and business
success. Its revolutionary design and outstanding quality, created a new trend in the U.S.
automobile industry, and customers simply loved the car. Yet, when the project was completed,
the project manager was fired. His “sin” was that project completion was delayed by six months.
In contrast, the second generation of Ford Taurus was developed in the early 1990s and
2
completed in 1995. With increased competition and the enormous success of Japanese imports,
Ford had hoped to reestablish Taurus, once again, as the best selling car in America. But the new
project manager learned the lesson of his predecessor: He considered project schedule as a “holy
grail,” and made sticking to the completion date the ultimate goal, while sacrificing other things.
Vendor relationships, team spirit, and product integration were just few of the issues that
suffered. The second generation of Taurus turned out to be a disappointing business experience.
It did not recapture the position of the best selling car in America and Ford was not able to repeat
its outstanding success of the first Taurus.

## Slide 79: Poker Metric: Percent of Hands Won

## Slide 80: Software Metric – On Time%

## Slide 81: Value Metric
Word Processing Market Share

## Slide 82: The Measurement Inversion
Lowest
Information Value
Highest Information Value
Most Measured
Least Measured
Cost & Time
Value Delivery

## Slide 83: Outputs and Outcomes
Ontime | No | Yes | No | Yes
Outcome | Bad | Good | Good | Bad

## Slide 84: Outputs and Outcomes
Outcome
Good
Bad
Output
Late
Ontime

## Slide 85
#9: Project success is determined by on-time delivery

## Slide 86
#10: Estimation is waste

## Slide 87: The Real Business Questions
Is it worth doing?
What is the priority?
When is the target time to ship?
What is the critical scope?
Do we have the right investment?
What is the cost of delay?

## Slide 88
#10: Estimation is waste

## Slide 89
Now What?

## Slide 90
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
Priority

## Slide 91: The A/B/C List sets proper expectations (similar to MoSCoW)
A | MUST be completed in order to ship the product and the schedule will be slipped if necessary to make this commitment.
B | Is WISHED to be completed in order to ship the product, but may be dropped without consequence.
C | Is NOT TARGETED to be completed prior to shipping, but might make it if time allows.
Only “A” features may be committed to customers.
If more than 50% of the planned effort is allocated to “A” items the project is at risk.

## Slide 92: Sizing for Scope Creep
500 Point release backlog
Velocity of 25 points per 2 week iteration
2%/mo = 1% scope creep per iteration = 5 pts.
Net Planned Velocity = 20 pts/iteration

## Slide 93: A/B/C List
A
50%
100%
Backlog Plan
Typical Delivery
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date

## Slide 94: A/B/C List
50%
100%
Backlog Plan
Uncertainty Risk
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date
A
Notes: Need some explanation to go along with this slide and the previous one.
--The idea is that there is uncertainty in the estimation process. A factor of 2X is a generally sufficient buffer if the team has gotten basic estimation down. Thus is it possible that what is actually delivered is only the “A” items. That is ok and actually expected.

## Slide 95: Metrics to Track

## Slide 96
Velocity
Scope Creep
Burnup Chart
Monitor Quality

## Slide 97: Ask the Team
Chart: 
| 40602 | 40607 | 40609 | 40612 | 40612 | 40617 | 40617 | 40618 | 40634 | 40648 | 40664 | 40664 | 40724
 | 0.038462 | 0.11538 | 0.19231 | 0.26923 | 0.34615 | 0.42308 | 0.5 | 0.57692 | 0.65385 | 0.73077 | 0.80769 | 0.88462 | 0.96154

## Slide 98: Cost of Delay

## Slide 99: Contact
Todd Little
  todd.little@ihs.com
  toddelittle@gmail.com
  www.toddlittleweb.com
  www.accelinnova.com
  www.linkedin.com/in/toddelittle/

## Slide 100: Overconfidence of Success
Chart: 
| Measured | Perceived
Project Success | 0.42 | 0.79
Matthew G. Miller, Ray J. Dawson, Kieran B. Miller, Malcolm Bradley (2008). New Insights into IT Project Failure & How to Avoid It. Presented at 22nd IPMA World Congress -­‐ Rome (Italy) November 9-­‐11, 2008, in Stream 6. As of May 2013, self published at http://www.mgmiller.co.uk/files/paper.pdf