## Slide 1: The Value Uncertainty Game
Sean Dunn, Enterprise Agile Coach, IHS
Chris Edwards, Sr. Manager, IHS
Todd Little, VP Product Development, IHS

## Slide 2: Purpose
A fun game to explore how risk and uncertainty impacts our decisions and behaviours in software development.

## Slide 3: Establishing Norms

## Slide 4: Introduce yourself to your new team (1 minute)

## Slide 6: Goal of the Game
Produce a Software Release in 3 iterations
Prioritize and re-prioritize the backlog to optimize value delivery before the fixed release date
Be the team that delivers the most points
  Delivered Value + “Commitment Points”

## Slide 7: Artifacts (5)
1 Score Card – Write Your Team’s
Number at the Top
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Value – Uncertainty Estimation Matrix
4 Dice
Iteration Plan
In Progress (WIP = 1)
Scrum Board
Accepted
14 User Stories
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice

## Slide 8: Roles (4)
Score Keeper – Update the score sheet after each day of the iteration
Sticky Minder – Move the Stories, keep the Scrum Board up-to-date
Dice Roller – Rolls the Dice

## Slide 9: Example Story
Fail; Story Not Accepted
Cost = 2 days
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice
Success; Story Completed
Day 1:
Day 2:
Value = 3 + 1 + 3 = 7
Notes: Read the story. Some stories will require you to roll 1 dice. Stories others 2 dice, 3 dice, etc…
Each story has a different way of calculating the value.

## Slide 10: Example: Relative Sizing
Value: Sum of all dice
Which story has a higher potential value?
Which story has a higher potential cost?
Test: Roll 3 dice – 2 or more dice are the same
ID 1
ID: 4 Value: product of dice
Test: Roll 3 dice - Three consecutive integers (straight)
Product > Sum
Pr(3 consecutive integers) < Pr(2 or more dice are the same)

## Slide 11: Clarification
ID: 5 Test: Roll 3 dice – no 1s and no 2s
Value: Sum of all dice
Meaning: None of the 3 dice are 1s or 2s

## Slide 12: Release Planning

## Slide 13
Estimation and Prioritization: Place stories by relative cost and value |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
ID: 4
ID:1
Notes: Find User Story #1, identified by the black border. Place Approximately in the “middle”. This is going to be our reference for relative estamiting.
Do this now.
We have just compared User Story #4 to User Story #1, and we know it is both larger in cost and value, so place it somewhere to the right and above User Story #1.
Do this now.
You will have 5 minutes to do this relative estimation with all other user stories. Like all estimates, it will be difficult to be precise, so you will have to make an educated guess.
Begin now.

## Slide 15: Mini-Retro
How is this like estimating in software?
How is it not like estimating in software?
What can we learn from this?

## Slide 16: Goal: Prioritize the backlog to maximize your team’s score by the end of the release

## Slide 17: Iteration Planning

## Slide 18: Stories and Scoring
Release is 3 iterations,
  10 “days” per iteration.
  1 Roll of the dice per day
WIP limit of one story in progress at a time
You can earn 5 extra “commitment” points for each COMMITTED story you deliver.
  Forfeit all commitment points for an iteration if any committed stories are missed.
Must commit to AT LEAST 3 stories per iteration.
You may choose to commit to more – BUT you lose ALL commitment points for that iteration if you miss ANY commitment.
Score = Delivered Value + Commitment Points

## Slide 19
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Plan the First Iteration
Iteration Plan
In Progress (WIP = 1)
Accepted
Must commit a minimum of 3 stories to each iteration
You can choose to commit more, but you forfeit all commitment points for that iteration if you miss any

## Slide 21: Simulation Example
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice

## Slide 22
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice

## Slide 23
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice

## Slide 24
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 1
Test: Roll 3 dice - 2 or more dice are the same
Value: Sum of all dice
7

## Slide 25
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 7
Test: Roll 3 Die – 2 or more 6’s
Value: Product of all dice
7
X

## Slide 26
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 7
Test: Roll 3 Die – 2 or more 6’s
Value: Product of all dice
7
X
X

## Slide 27
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 7
Test: Roll 3 Die – 2 or more 6’s
Value: Product of all dice
7
X
X
36

## Slide 28
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 14
Test: Roll 2 Dice – Both Dice are Different
Value: Highest of two dice
7
X
X
36
X

## Slide 29
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 14
Test: Roll 2 Dice – Both Dice are Different
Value: Highest of two dice
7
X
X
36
X
4

## Slide 30
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 9
Test: Roll 1 Dice – Not a 1
Value: Value of Single Die
7
X
X
36
X
4
x

## Slide 31
Iteration Plan
In Progress (WIP = 1)
Accepted
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3
X
X
ID: 9
Test: Roll 1 Dice – Not a 1
Value: Value of Single Die
7
X
X
36
X
4
X
6
53
4
Yes
15

## Slide 32
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 4 | X | X | X | 10 | X | 3 | X | X | 3 | X | 16 | 3 | NO | 0
3
X
X
7
X
X
36
X
4
X
6
53
4
Yes
15

## Slide 33
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 4 | X | X | X | 10 | X | 3 | X | X | 3 | X | 16 | 3 | NO | 0
3 | 4 | X | X | 10 | X | 2 | 3 | X | 14 | X | X | 29 | 4 | Yes | 20
3
X
X
7
X
X
36
X
4
X
6
53
4
Yes
15

## Slide 34
 | # Stories Committed to Iteration | Roll (Day) |  |  |  |  |  |  |  |  |  | Total of Accepted Value | # Stories Completed | Iteration Commitment Met?(Yes/No) | Commitment Points
Iteration |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | 4 | X | X | X | 10 | X | 3 | X | X | 3 | X | 16 | 3 | NO | 0
3 | 4 | X | X | 10 | X | 2 | 3 | X | 14 | X | X | 29 | 4 | Yes | 20
3
X
X
7
X
X
36
X
4
X
6
53
4
Yes
15
98
35
Total Score = 133

## Slide 35: Special Actions
It is ok abandon a story
  You can come back to it later
You can not redo a story once it has been accepted

## Slide 37: Story Strategies
How did you choose which story to pick?
Did you abandon a story in the middle of an iteration?
Did you change your strategy at any point?

## Slide 38: Retrospective
What did you learn?
What elements were like software development?
What elements are different in software development?
What impact did committing have on your behavior and decision?

## Slide 39: How did committing influence your decisions?

## Slide 40
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
Priority
Notes: How would we prioritize these stories?
Stories that have high value, at low cost, should easily come first. This area in the green.
Now as we decend through priority, we get thorugh this yellow zone. Do you take a small story with low payoff, or a risky story with high potential payoff? That’s a decision your team can make.
Expensive stories with low payoff, we oviously payoff really low.
There are many decision to be made here.

## Slide 41: So what do the statistics say?

## Slide 42
Chart: Value vs Cost
| 2.25 | 10.285714285714285 | 6 | 9 | 3.375 | 3.375 | 13.5 | 1.44 | 1.2 | 1.2 | 8 | 3.5999999999999996 | 4.1538461538461542 | 1.2
Value | 10.5 | 70 | 15.1667 | 52.5 | 13.5 | 7.5 | 114.75 | 3.8 | 4 | 3 | 15 | 14 | 14 | 4.6667

## Slide 43
Chart: Expected Value vs Cost
| 2.25 | 10.285714285714285 | 6 | 9 | 3.375 | 3.375 | 13.5 | 1.44 | 1.2 | 1.2 | 8 | 3.5999999999999996 | 4.1538461538461542 | 1.2
Ave/Attempt | 4.6667 | 6.8056 | 2.5278 | 5.8333 | 4 | 2.2222 | 8.5 | 2.6389 | 3.3333 | 2.5 | 1.875 | 3.8889 | 3.3704 | 3.8889

## Slide 44: Running a Monte Carlo Simulation
Two Strategies:
  Prioritize lowest cost (meet commitments)
  Prioritize highest expected value (deliver most value)

## Slide 45
Chart: Accepted Story Count Histogram
| 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14
Easiest First | 0 | 0 | 0 | 0 | 17 | 43 | 33 | 7
Highest Expected Value First | 8 | 35 | 19 | 14 | 8 | 9 | 5 | 2

## Slide 46
Chart: Accepted Points Histogram
| 0 | 50 | 100 | 150 | 200 | 250 | 300 | 350 | 400 | 450 | 500
Easiest First | 0 | 3 | 60 | 26 | 4 | 3 | 3 | 0 | 0 | 0 | 0
Highest Expected Value First | 8 | 7 | 5 | 14 | 13 | 22 | 7 | 14 | 7 | 2 | 1

## Slide 47: How do the strategies compare
 | Easiest-First | Highest Expected Value First
Average Delivered Value Points | 104 | 202
Commitment Points | 25 | 9
On average, always choosing the highest expected value story (and sticking with it) will deliver twice as much value as always going with the easiest stories. On average, this strategy will only cost you 16 commitment points.

## Slide 48: Where is an example of incentivizing sub-optimal decisions?
Why should we not just always be working on the highest-priority thing?

## Slide 49
Estimation and Prioritization |  |  |  | 
XL |  |  |  | 
L |  |  |  | 
M |  |  |  | 
S |  |  |  | 
 | S | M | L | XL
Cost
Value
De-Risk?
Notes: How would we prioritize these stories?
Stories that have high value, at low cost, should easily come first. This area in the green.
Now as we decend through priority, we get thorugh this yellow zone. Do you take a small story with low payoff, or a risky story with high potential payoff? That’s a decision your team can make.
Expensive stories with low payoff, we oviously payoff really low.
There are many decision to be made here.

## Slide 50: How Can Reduce Risk?
Split stories
Get customer feedback early

## Slide 51: Summary
Uncertainty is an unavoidable aspect of software development
Commitments may influence decisions

## Slide 52: Contact
Todd Little
  todd.little@ihs.com
  www.toddlittleweb.com
Sean Dunn
  sean.dunn@ihs.com
  @SeanDunn10
Chris Edwards
  chris.edwards@ihs.com
  @AgileChrisYYC
  Source Code for Monte Carlo Simulation: github.com/cjsedwards/ValueUncertaintyGame