## Slide 1: Dealing with Estimation, Uncertainty, Risk, and Commitment : An Outside-In Look at Agility and Risk Management
Todd Little
Sr. Development Manager
Landmark Software & Services
Notes: Todd comes from Oil and Gas exploration, a business that deals with risk in many facets. Chris comes from investment banking, another area that has made it important to understand and comprehend issues associated with risk. Both Todd and Chris have spent their careers developing software in these industries.

## Slide 2: Risky Business

## Slide 3: Hurricane Rita
Notes: What can we say about every one of these predictions? They are wrong. But the collective set of predictions is quite useful. Which is more important when predicting hurricanes – where it hits or when it hits? Ok, both are important, but where is much more important than when. If you are in Florida you don’t really care when it hits. But once you know it has a chance to hit Houston then it is very important to know when it might hit.

## Slide 4: Managing the Coming Storm Inside the Tornado
When will we get the requirements?
All in good time, my little pretty, all in good time
But I guess it doesn't matter anyway
Doesn't anybody believe me?
You're a very bad man!
Just give me your estimates by this afternoon
No, we need something today!
I already promised the customer it will be out in 6 months
No, we need it sooner.
Not so fast! Not so fast! ... I'll have to give the matter a little thought. Go away and come back tomorrow
Ok then, it will take 2 years.
Team Unity
Project Kickoff
Notes: We look at a typical software project…..

## Slide 5: We’re not in Kansas Anymore
My! People come and go so quickly here!
I may not come out alive, but I'm goin' in there!
The Great and Powerful Oz has got matters well in hand.
"Hee hee hee ha ha! Going so soon? I wouldn't hear of it! Why, my little party's just beginning!
Developer Hero
Reorg
Testing

## Slide 6: How do “Risky Businesses” work
“It’s tough to make predictions, especially about the future.” Yogi Berra, Niels Bohr

## Slide 7: War
They couldn't hit an elephant at this dist…
General John B. Sedgwick, Union Army Civil War officer's last words, uttered during the Battle of Spotsylvania, 1864
Notes: War – now that’s an area with lots of risk. I guess he didn’t do too well in his prediction.

## Slide 8: Gordon the Guided Missile

## Slide 9: Movies
78% of Films Lose Money
6% of films make 80% of profit
Notes: Most movies strive to be the next Titanic, the largest grossing film of all time.
The reality is that the vast majority really do end up closer to the real Titanic than to the movie Titanic.

## Slide 10: Books
300,000 books
in print 2004,
<25% sold more
Than 100 copies
Notes: Books. Here is my book. Doesn’t it look like it is chock full of useful stuff?
But only 25% of books sell more than 100 copies. Please do your part so that I am not part of that statistic.

## Slide 11: Poker

## Slide 12: Texas Hold’em: Which is the best hole hand?
33.5%
29.6%
36.5%
A
B
C

## Slide 13: Poker Metric: Percent of Hands Won

## Slide 14: Oil & Gas Exploration
90-80% Failure
Notes: Oil exploration is highly risky. It used to be that 10% was a good find rate for wildcat wells. Based on improvements in technology this is closer to 20%. Still risky, but that risk is acceptable because the payout is enormous. The key is having a diversified portfolio to balance the risk exposure.

## Slide 15
Notes: Which risks are important? The sharp edges of the sign or the fact that the bridge is out ahead?

## Slide 16: Which Risks Are Important
Notes: Oil and gas geologists and engineers build models to help them comprehend the uncertainties. This is a tornado chart, because it looks like a tornado. This chart clearly shows that the largest uncertainty is associated with Reserves, with the next largest uncertainty being oil/gas price. This gives the engineer something to focus on. Perhaps there is additional data that can be collected to help reduce the uncertainty bars. There may not be anything that can be done about Oil/gas price. Perhaps futures contracts could be used to hedge some of the uncertainty. The other uncertainties may not be worth spending too much time since they have limited effect on the total uncertainty.

## Slide 17: Real Options
The right — but not the obligation — to undertake certain actions prior to an expiry date

## Slide 18: Airline Tickets

## Slide 20: Real Options
The right, but not the obligation to take some action prior to an expiry date

## Slide 21: Real Options
Value of Information
Value of Flexibility

## Slide 22: Options

## Slide 23: Value of Information

## Slide 24: Value of Information

## Slide 25: Value of Flexibility

## Slide 26: Making An Agile Conference Agile
Chart: Submissions for 2011 compared to 2010
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Y2010 | 916 | 899 | 810 | 629 | 547 | 496 | 453 | 412 | 387 | 367 | 327 | 301 | 278 | 260 | 237 | 227 | 219 | 210 | 197 | 190 | 177 | 163 | 151 | 144 | 131 | 120 | 115 | 106 | 93 | 89 | 84 | 82 | 80 | 73 | 68 | 62 | 57 | 53 | 50 | 46 | 40 | 33 | 32 | 30 | 26 | 23 | 18 | 10 | 1
Y2011-IT1 | 473 | 282 | 171 | 146 | 116 | 96 | 72 | 63 | 49 | 46 | 42 | 40 | 38 | 31 | 23 | 17 | 13 | 0 | 9 | 9 | 7 | 7 | 5 | 0 | 4 | 1
Y2011-IT2 | 938 | 785 | 732 | 714 | 687 | 672 | 657 | 647 | 612 | 604 | 599 | 593 | 588 | 572 | 571 | 561 | 556 | 555 | 551 | 546 | 544 | 538 | 534 | 531 | 529 | 523 | 522 | 516 | 510 | 505 | 504 | 502 | 495 | 492 | 488
5 Extra weeks to review sessions

## Slide 27
Chart: Estimated Agile 2010 Attendance
| 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | FINAL
Most Likely | 1400 | 1364.5243 | 1120.1596 | 971.8365 | 1047.0469 | 1111.6133 | 1255.6124 | 1241.4581 | 1280.5708 | 1251.8608 | 1272.45 | 1295.6802 | 1330.7759 | 1396.1783 | 1430.0961 | 1418.2858 | 1336
Pessimistic | 1200 | 1178.5951 | 939.7996 | 797.7668 | 889.4518 | 969.3672 | 1129.9984 | 1128.1304 | 1180.5262 | 1163.8541 | 1197.2486 | 1233.2142 | 1281.0642 | 1359.338 | 1405.7486 | 1406.1182 | 1336
Optimistic | 1700 | 1643.418 | 1390.6995 | 1232.9411 | 1283.4394 | 1324.9825 | 1444.0333 | 1411.4497 | 1430.6377 | 1383.8708 | 1385.252 | 1389.3793 | 1405.3435 | 1451.4388 | 1466.6173 | 1436.5372 | 1336

## Slide 28: Do you have a choice?
Option
Commitment
Decision

## Slide 29
Notes: http://www.flickr.com/photos/nick_anderson/5049751331/sizes/m/in/photostream/

## Slide 30: Agile projects need risk management too

## Slide 31
Categories of risk
Delivery Failure
Business Case
Failure
Collateral Damage
Political Risk
Quality and Market
Acceptance
Notes: We have found it useful to categorize risk into 3 primary categories.
Delivery Failure
Business Case Failure
And Collateral Damage

## Slide 32: Two Risk Perspectives
Individual
Perspective
Business
Perspective

## Slide 33: Delivery Failure
Late
Over Budget

## Slide 34: Delivery Challenges/Failures
Standish Group 2006, reported by CEO Jim Johnson, CIO.com, ‘How to Spot a Failing Project’
Notes: Delivery failures are well documented in the software business.
This is the classic report from Standish showing only 35% of projects delivered on time with expected features. 46% were challenged and 19% were killed. This is from 2006, and is a substantial improvement from the 19% success rate in 1996.

## Slide 35: Why is Software Late? Genuchten 1991 IEEE
General Manager | Project Manager | Item
1 | 10 | Insufficient front end planning
2 | 3 | Unrealistic project plan
3 | 8 | Project scope underestimated
4 | 1 | Customer/management changes
5 | 14 | Insufficient contingency planning
6 | 13 | Inability to track progress
7 | 5 | Inability to track problems early
8 | 9 | Insufficient Number of checkpoints
9 | 4 | Staffing problems
10 | 2 | Technical complexity
11 | 6 | Priority Shifts
12 | 11 | No commitment by personnel to plan
13 | 12 | Uncooperative support groups
14 | 7 | Sinking team spirit
15 | 15 | Unqualified project personnel

## Slide 36: The Context of Feedback

## Slide 37: Why is Software Late? Genuchten 1991 IEEE
General Manager | Project Manager | Item
4 | 1 | Customer/management changes
10 | 2 | Technical complexity
2 | 3 | Unrealistic project plan
9 | 4 | Staffing problems
7 | 5 | Inability to track problems early
11 | 6 | Priority Shifts
14 | 7 | Sinking team spirit
3 | 8 | Project scope underestimated
8 | 9 | Insufficient Number of checkpoints
1 | 10 | Insufficient front end planning
12 | 11 | No commitment by personnel to plan
13 | 12 | Uncooperative support groups
6 | 13 | Inability to track progress
5 | 14 | Insufficient contingency planning
15 | 15 | Unqualified project personnel
Notes: The project manager is much closer to the actual work being done and so I tend to think their response is closer to reality. What is of particular interest is where there is a discrepancy between the General Manager and the Project Manager.
1 4 Customer/management changes
PM: They were constantly changing their minds GM:OK, so we changed a few things once in a while
2 10 Technical complexity
PM: We were using new technology and had to discover all the limitations GM: I just to them to make it look like that cool demo I saw
3 2 Unrealistic project plan
PM: We told them it would take longer GM: I had to push them so that they would be serious
4 9 Staffing problems
PM: We couldn’t get the people we needed GM: I gave them everyone I had available
5 7 Inability to track problems early
PM/GM: agree --- We didn’t know what we didn’t know
6 11 Priority Shifts
PM: They were constantly changing their minds GM: We didn’t change that much
7 14 Sinking team spirit
PM: The team felt overworked and underappreciated GM: We’ve got a great team. What spirit they have
8 3 Project scope underestimated
PM: I didn’t really feel that we underestimated it. We told them it would be hard GM: We really didn’t think it was such a big project
9 8 Insufficient Number of checkpoints
PM/GM agree – it would have been good to have better visibility into what was going on
10 1 Insufficient front end planning
PM: We had a plan, but they didn’t like the answer and kept changing their mind GM: It all would have been fine if we could have just planned better
11 12 No commitment by personnel to plan
PM/GM agree – team was willing to commit
12 13 Uncooperative support groups
PM/GM agree – support groups were willing to help
13 6 Inability to track progress
PM: We had pretty good tracking GM: I wish I had better visibility into what was going on so I could have done something
14 5 Insufficient contingency planning
PM: We had decent contingency planning, we just weren’t able to do anything GM: We just needed better planning
15 15 Unqualified project personnel
PM/GM agree – people are our most important assets

## Slide 38: Why is Software Late? Genuchten 1991 IEEE
General Manager | Project Manager | Item
H | H | Customer/management changes
L | H | Overall complexity
H | H | Unrealistic project plan
M | H | Staffing problems
H | L | Insufficient front end planning
Notes: The project manager is much closer to the actual work being done and so I tend to think their response is closer to reality. What is of particular interest is where there is a discrepancy between the General Manager and the Project Manager.
1 4 Customer/management changes
PM: They were constantly changing their minds GM:OK, so we changed a few things once in a while
2 10 Technical complexity
PM: We were using new technology and had to discover all the limitations GM: I just to them to make it look like that cool demo I saw
3 2 Unrealistic project plan
PM: We told them it would take longer GM: I had to push them so that they would be serious
4 9 Staffing problems
PM: We couldn’t get the people we needed GM: I gave them everyone I had available
5 7 Inability to track problems early
PM/GM: agree --- We didn’t know what we didn’t know
6 11 Priority Shifts
PM: They were constantly changing their minds GM: We didn’t change that much
7 14 Sinking team spirit
PM: The team felt overworked and underappreciated GM: We’ve got a great team. What spirit they have
8 3 Project scope underestimated
PM: I didn’t really feel that we underestimated it. We told them it would be hard GM: We really didn’t think it was such a big project
9 8 Insufficient Number of checkpoints
PM/GM agree – it would have been good to have better visibility into what was going on
10 1 Insufficient front end planning
PM: We had a plan, but they didn’t like the answer and kept changing their mind GM: It all would have been fine if we could have just planned better
11 12 No commitment by personnel to plan
PM/GM agree – team was willing to commit
12 13 Uncooperative support groups
PM/GM agree – support groups were willing to help
13 6 Inability to track progress
PM: We had pretty good tracking GM: I wish I had better visibility into what was going on so I could have done something
14 5 Insufficient contingency planning
PM: We had decent contingency planning, we just weren’t able to do anything GM: We just needed better planning
15 15 Unqualified project personnel
PM/GM agree – people are our most important assets

## Slide 39: Da Plan, Boss – Da Plan

## Slide 40: IEEE Software, May/June 2006
Notes: This is from an IEEE Software article that I published in May 2006

## Slide 41: Accuracy of Initial Estimate
Chart: Initial Estimate vs. Actual Duration
| 0 | 1000
Ideal | 0 | 1000
DeMarco | 231 | 477 | 269 | 750 | 249 | 147 | 204 | 395 | 837 | 529 | 584 | 729 | 824 | 946 | 575 | 457 | 353 | 277 | 786 | 184

## Slide 42: Uncertainty Bounds
Chart: Cumulative Distribution Function of Actual/Estimate Ratio
| 0.62314540059347479 | 0.63489950752030033 | 0.759457933370978 | 0.8652514997692663 | 1.033623910336239 | 1.1229946524064141 | 1.1518915866741932 | 1.4538093485461876 | 1.8247220405493778 | 1.8933428775948462 | 1.9447219447219461 | 2.0391608391608367 | 2.0808080808080787 | 2.6543209876543212 | 2.7804642166344355 | 2.8652037617554882 | 3.0856643356643354 | 3.4029484029483981 | 3.8833992094861682 | 4.9197860962566864
DeMarco Data | 0.025 | 0.075 | 0.125 | 0.175 | 0.225 | 0.275 | 0.325 | 0.375 | 0.425 | 0.475 | 0.525 | 0.575 | 0.625 | 0.675 | 0.725 | 0.775 | 0.825 | 0.875 | 0.925 | 0.975
DeMarco Log-Normal | 0.047419 | 0.05051 | 0.088876 | 0.12819 | 0.19908 | 0.23896 | 0.252 | 0.38649 | 0.53276 | 0.55663 | 0.57382 | 0.6039 | 0.61656 | 0.75602 | 0.77914 | 0.7934 | 0.82618 | 0.86408 | 0.90562 | 0.95545
10-20% on time
10% exceed 3-4x
Median project 1.7x

## Slide 43: How does Estimation Accuracy Improve Over Time?
Chart: Cone of Uncertainty from Boehm
| Feasibility | Concept of Operation | Requirements Spec | Product Design Spec | Detail Design Spec | Accepted Software
 | -0.60206 | -0.30103 | -0.17609 | -0.09691 | -0.041393 | 0
 | 0.60206 | 0.30103 | 0.17609 | 0.09691 | 0.041393 | 0
Notes: The conventional wisdom is that estimation gets better as the project progresses. This was first stated by Barry Boehm in COCOMO II, and stated by many authors subsequently, most notably Steve McConnell. At the Feasibility state the uncertainty band is 16X, while at Concept it has narrowed to 4X and by the Requirements it has reduced to 2.25X. This makes a lot of sense.

## Slide 44: Landmark Cone of Uncertainty
Chart: Estimation Error over Time

## Slide 45: But is Uncertainty Really Reduced?
“Take away an ordinary person’s illusions and you take away happiness at the same time.”
Henrik Ibsen--Villanden

## Slide 46: Remaining Uncertainty

## Slide 47: Sources of Error
Bias
Uncertainty Range
Scope Creep

## Slide 48: Sources of Error
Bias
Median
Mean
Estimate

## Slide 49: Negotiation Bias
"It is difficult to get a man to understand something when his salary depends upon his not understanding it.“
        Upton Sinclair:

## Slide 50: Politics and Schedule Estimation
http://www.stevemcconnell.com/ieeesoftware/bp03.htm
Developers tend to be temperamentally opposed to the use of negotiating tricks. Such tricks offend their sense of technical accuracy and fair play. Developers don't want to offer lopsidedly high initial estimates even when they know that customers, marketers, or bosses will start with lopsidedly low bargaining positions.
  Steve McConnell

## Slide 51: Test 1 (Jørgensen)
Group | Guidance | Result
A | 800 | 
B | 40 | 
C | 4 | 
D | None | 160

## Slide 52: Test 1
Group | Guidance | Result
A | 800 | 300
B | 40 | 100
C | 4 | 60
D | None | 160

## Slide 53: Test 2
Group | Guidance | Result
A | Minor Extension | 
B | New Functionality | 
C | Extension | 50

## Slide 54: Test 2
Group | Guidance | Result
A | Minor Extension | 40
B | New Functionality | 80
C | Extension | 50

## Slide 55: Understand Bias
"What gets us into trouble is not what we don't know. It's what we know for sure that just ain't so.“
        Mark Twain

## Slide 56: Velocity/Cycle Time Helps Remove Bias
Chart: 
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Projected Ship Date | 40086 | 40433.1 | 40207.6696 | 40138.0244 | 40087.44 | 40140.6185 | 40120.7566 | 40120.7566

## Slide 57: But Velocity is not a Silver Bullet
Story Estimate

## Slide 58: Sources of Error
Range of Uncertainty

## Slide 59: Estimation Errors
Lan Cao - Estimating Agile Software Project Effort: An Empirical Study

## Slide 60: Lan Cao - Estimating Agile Software Project Effort: An Empirical Study
2X
Uncertainty,
Notes: Lessons learned: If uncertainty is high, work on it earlier. Reduce Technical Debt—Get to potentially shippable at each iteration. Finding and fixing the last bugs has high uncertainty – plan on there being uncertainty.

## Slide 61: Sources of Error
Scope Creep

## Slide 62: We want this
Efficiency
Predictability
Social Networking
Agile
Late projects
Integration
Revenue
BPM
SOA
Mobility
CLOUD
Innovation
Business
Intelligence
Notes: Chris taped one of the investment bankers at his previous job

## Slide 63: Uncertainty Bounds
Chart: Cumulative Distribution Function of Actual/Estimate Ratio
| 0.62314540059347479 | 0.63489950752030033 | 0.759457933370978 | 0.8652514997692663 | 1.033623910336239 | 1.1229946524064141 | 1.1518915866741932 | 1.4538093485461876 | 1.8247220405493778 | 1.8933428775948462 | 1.9447219447219461 | 2.0391608391608367 | 2.0808080808080787 | 2.6543209876543212 | 2.7804642166344355 | 2.8652037617554882 | 3.0856643356643354 | 3.4029484029483981 | 3.8833992094861682 | 4.9197860962566864
DeMarco Data | 0.025 | 0.075 | 0.125 | 0.175 | 0.225 | 0.275 | 0.325 | 0.375 | 0.425 | 0.475 | 0.525 | 0.575 | 0.625 | 0.675 | 0.725 | 0.775 | 0.825 | 0.875 | 0.925 | 0.975
DeMarco Log-Normal | 0.047419 | 0.05051 | 0.088876 | 0.12819 | 0.19908 | 0.23896 | 0.252 | 0.38649 | 0.53276 | 0.55663 | 0.57382 | 0.6039 | 0.61656 | 0.75602 | 0.77914 | 0.7934 | 0.82618 | 0.86408 | 0.90562 | 0.95545
10-20% on time
10% exceed 3-4x
Median project 1.7x

## Slide 64: The A/B/C List sets proper expectations
A | MUST be completed in order to ship the product and the schedule will be slipped if necessary to make this commitment.
B | Is TARGETED to be completed in order to ship the product, but may be dropped without consequence.
C | Is NOT TARGETED to be completed prior to shipping, but might make it if time allows.
Only “A” features are commitments.
If more than 50% of the planned effort is allocated to “A” items the project is at risk.

## Slide 65: A/B/C List
A
50%
100%
Backlog Plan
Typical Delivery
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date

## Slide 66: A/B/C List
A
50%
100%
Backlog Plan
Typical Delivery
25%
A
B
C
B
C
D
50%
25%
Target Delivery Date

## Slide 67: A/B/C List
50%
100%
Backlog Plan
Uncertainty Risk
25%
A
B
C
50%
25%
Target Delivery Date
A
Notes: Need some explanation to go along with this slide and the previous one.
--The idea is that there is uncertainty in the estimation process. A factor of 2X is a generally sufficient buffer if the team has gotten basic estimation down. Thus is it possible that what is actually delivered is only the “A” items. That is ok and actually expected.

## Slide 68: Product Innovation Flow
Adaptive Activities
Project Sanction
RTM
CORE Activities
Idea Filter
Hot Items
A
Backlog Burnup
Sales
Services
Customer
Support
Product
Backlog
A
Items
Iteration
Backlog
Flexible Scope
Backlog
Newly Discovered
Items
Most Items for consideration in next release
B & C
Release
Backlog
B/C/D

## Slide 69: No Surprises!
Risk Management = Expectation Management

## Slide 70: Iteration Review Questions
What promises have been made, to whom were they made, and who made them?
What key decisions or commitments might we have to make within the next 2 iterations?
Questions to ask team anonymously
  When will we be ready to ship?
  Will we be able to keep our promises?
  Is the team healthy and operating effectively?
  Is the team on the right path?

## Slide 71: Ask the Team When They Believe They Will Finish
Chart: 
| 40602 | 40607 | 40609 | 40612 | 40612 | 40617 | 40617 | 40618 | 40634 | 40648 | 40664 | 40664 | 40724
 | 0.038462 | 0.11538 | 0.19231 | 0.26923 | 0.34615 | 0.42308 | 0.5 | 0.57692 | 0.65385 | 0.73077 | 0.80769 | 0.88462 | 0.96154

## Slide 72: Cost of Delay

## Slide 73: Tools for Delivery Risk
Chart: 
| 40602 | 40607 | 40609 | 40612 | 40612 | 40617 | 40617 | 40618 | 40634 | 40648 | 40664 | 40664 | 40724
 | 0.038462 | 0.11538 | 0.19231 | 0.26923 | 0.34615 | 0.42308 | 0.5 | 0.57692 | 0.65385 | 0.73077 | 0.80769 | 0.88462 | 0.96154
Stop Dreaming
Ask the Team
Cost of Delay

## Slide 74: Delivery Risk
Business Perspective | Individual Perspective
Cost of Delay Business Credibility | Personal Credibility

## Slide 75: Collateral Damage
11 hour wait time
20-30 deaths
Notes: In October 1992, the London Ambulance Service suffered a disaster that brought their operations to a virtual standstill over 36 hours, and up to 20-30 people may have died as a result of ambulances arriving too late on the scene. Upon further investigation, it was discovered that the new computer aided dispatch (CAD) software was responsible for the crisis. The problem lay in the design of the software, which was completely inadequate for the needs of the London Ambulance Service. So terribly pathetic were this software's services that response times to emergency calls were as high as 11 hours during the 36 hours crisis.

## Slide 76: Delivery Failure results in Collateral Damage
Notes: When the Denver Airport baggage handling system was designed, for example, no one asked what would happen if the fully automated system failed. How would baggage be handed? No one thought about it and there we no accommodations made in the airport plan. So when the system did fail there were no other alternatives to move baggage around the airport. There were no underground roadways on which to manually move luggage using tugs.

## Slide 77: Titanic
Time pressure
Feedback blocks
Unsinkable

## Slide 78
I’m beginning to think it wasn’t such a good idea to turn off those unit tests
Notes:   Safety is not to be messed with.
  Test, Test, Test
  Test again with real data
  Test, Test, Test
  Test again with real data

## Slide 79: Collateral Damage
Business Perspective | Individual Perspective
Could be catastrophic | Some individuals may be willing to take on more risk than desired

## Slide 80
Collateral Damage Management
An effective roll-back strategy
Honor feedback
Inspect
Incremental Delivery
Notes:   Rollback plan

## Slide 81: Business Case Failure

## Slide 82: Business Case Failure
Notes: But what if we deliver on time but the market doesn’t care? This is the classic case of Iridium. Huge undertaking, huge failure. The phones were huge, over a pound. The phones didn’t work inside buildings—not very useful. And the cost were prohibitive.

## Slide 83
Always or Often Used: 20%
Never or Rarely Used: 64%
Sometimes
16%
Rarely
19%
Never
45%
Often
13%
Always
7%
Features and Functions
Standish Group Study, reported by CEO Jim Johnson, XP2002
Notes: 83
Project delivers but fails to deliver value.

## Slide 84
Powerful Questions are:
What are we building?
What Business are we in?
What Building are we in?

## Slide 85: The Purpose Alignment Model
Notes: [Purpose of slide] [#]
  [Information]

## Slide 86: In Practice
CAN WE
CREATE A
DIFFERENTIATED
PARTNERSHIP?
INNOVATE,
CREATE
MINIMIZE /
ELIMINATE
ACHIEVE AND
MAINTAIN PARITY, MIMIC, SIMPLIFY
Notes: [Purpose of slide] [#]
  [Information]

## Slide 87: Applicable at all Levels
Corporate Strategy
Product Strategy

## Slide 88: A View of Strategy - Apple
88
ATT
NEW PRODUCT DESIGN
USER EXPERIENCE
CONTENT DISTRIBUTION
MS OFFICE
INTEL HARDWARE
OTHER SOFTWARE
PERIPHERALS
Notes: 88
[Purpose of slide] [#]
  [Information]
© International Institute of Business Analysis®

## Slide 89: Business Case
Business Perspective | Individual Perspective
Sustainable competitive advantage | How can I sell this so that I can get more budget?

## Slide 90: Market Acceptance
Features and Quality

## Slide 91: Market Acceptance

## Slide 92: The Cone of Uncertainty
We expect uncertainty and manage for it through iterations, anticipation, and adaptation.
Notes: Inspection and adaptation is the answer. Iterations help bring in new information

## Slide 93: “I skate to where the puck is going to be, not where it has been.”

## Slide 94: Quality and Market Acceptance Strategies
Seek and honor feedback
Incremental Delivery

## Slide 95
Notes: Which risks are important? The sharp edges of the sign or the fact that the bridge is out ahead?

## Slide 96: Wrong Priorities
Notes: The first generation of Ford Taurus turned out to be the best selling car in America in the
late 1980s. Conceived in the 1980's and introduced in 1986, it set the standard for new practices
in project management and product development. It was one of the early projects in the U.S.,
which fully utilized the concept of cross-functional teams and concurrent engineering practices.
It established close ties with vendors and subcontractors, and was characterized by a spirit of
cooperation and strong synergy among teams. The result was a remarkable market and business
success. Its revolutionary design and outstanding quality, created a new trend in the U.S.
automobile industry, and customers simply loved the car. Yet, when the project was completed,
the project manager was fired. His “sin” was that project completion was delayed by six months.
In contrast, the second generation of Ford Taurus was developed in the early 1990s and
2
completed in 1995. With increased competition and the enormous success of Japanese imports,
Ford had hoped to reestablish Taurus, once again, as the best selling car in America. But the new
project manager learned the lesson of his predecessor: He considered project schedule as a “holy
grail,” and made sticking to the completion date the ultimate goal, while sacrificing other things.
Vendor relationships, team spirit, and product integration were just few of the issues that
suffered. The second generation of Taurus turned out to be a disappointing business experience.
It did not recapture the position of the best selling car in America and Ford was not able to repeat
its outstanding success of the first Taurus.

## Slide 97: Compute This
"I recently asked a colleague [CIO] whether he would prefer to deliver a project somewhat late and over-budget but rich with business benefits or one that is on-time and underbudget but of scant value to the business. He thought it was a tough call, and then went for the on-time scenario. Delivering on-time and within budget is part of his IT department's performance metrics. Chasing after the elusive business value, over which he thought he had little control anyway, is not."
Cutter Sr. Consultant Helen Pukszta

## Slide 98: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  | ██ | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  | █ | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 99: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ | ███ | ███ | ███ | ███ | 
Schedule Uncertainty |  |  |  | ███ | ███ | ██ |  |  |  | 
General Market Uncertainty |  |  |  |  | ██ | ██ |  |  |  | 
Cost Uncertainty |  |  |  |  | ██ | █ |  |  |  | 

## Slide 100: Software Tornado Example
Item | -15M |  | 0M |  | 15M |  | 30M |  | 45M | 
Product Acceptance Uncertainty |  |  |  | ███ | ███ |  |  |  |  | 
Schedule Uncertainty |  |  |  | ███ | ██ |  |  |  |  | 
General Market Uncertainty |  |  |  | ██ | ██ |  |  |  |  | 
Cost Uncertainty |  |  |  | ██ | █ |  |  |  |  | 

## Slide 101: Software Metric: Projects Delivered On Time

## Slide 102: Market Acceptance
Business Perspective | Individual Perspective
Impact to revenue Impact to credibility Cost of rework | Priorities are often guided by other perceived constraints

## Slide 103: Political Risk

## Slide 104: Change or Maintain

## Slide 105: Political Challenges
Boss and above | Boss’s Peers | Boss’s Indirect Peers
You | Peers | Indirect Peers
Direct Reports | Peers’ Reports | Indirect

## Slide 106: Network
What’s in it for them for everyone to succeed?
What do they worry about losing if you are successful?

## Slide 107: Long Ago and Far, Far Away…

## Slide 109: Collaborating with Non-Collaborators
Agreement
Disagree
Agree
Collaboration
Non-
Collaborator
Collaborator
Compliance
Combative
Creative
Tension
Collegial
Common Practice
More useful
Drive to
Purpose

## Slide 110: Agile Leadership

## Slide 111: Politics
Business Perspective | Individual Perspective
Politics do not add to business value other than by luck | Perception trumps Reality Politics forms Perception

## Slide 112: Final Summary
Risk | Business Perspective | Individual Perspective | Tools
Collateral Damage | Could be catastrophic | Make or Break career. Individuals may be willing to take more risk than the organization | • Build quality in • Feedback loops
Business Case | Strategic alignment with market need | Demonstrate Confidence | • Purpose Alignment Model
Delivery of Market/ Quality Need | Impact to revenue Impact to credibility Cost of rework | Depends on the individual - Priorities are often guided by other perceived constraints | • Customer Feedback
Delivery on Time or within Budget | Cost of Delay Reduction of ROI Business Credibility | Personal credibility | • Cost of Delay • Tornado Charts
Politics | Markets only care if politics influence external perception. | Perception trumps Reality Politics forms Perception | • Networking & Transparency • Collaborating with Non-Collaborators

## Slide 113: Risk Management is not Risk Aversion

## Slide 114: Contact
Todd Little
  todd@toddlittleweb.com
  www.toddlittleweb.com
  www.accelinnova.com